americanflat

Operations

90-Day AI Readiness Plan

June 2026

The Team Right Now

| Anthony | Iván | John | Carolina |
| --- | --- | --- | --- |
| 10 | 10 | 8 | 7 |

| Umer | Erickson | Nica |
| --- | --- | --- |
| 3 | 3 | 2 |

The Gap

3 builders ¦ 3 ramping ¦ 1 director

Builders ship skills. Ramping team: understands AI but hasn't led a workflow yet.

90 Days. Three Moves.

| Days 1–30 Stabilize Erickson & Nica join BTR task daily with John & Carolina. Document critical knowledge. | Days 31–60 Systematize Each person owns an AI agent in their domain. Ship first end-to-end workflows. | Days 61–90 Scale Contingency planning for John (WH backup). Headcount & role review. |
| --- | --- | --- |

Key Risks

| John | WH ops + skill-building both go dark if he leaves. |
| --- | --- |

| Iván | Platform + security in one head. Daily firefighting eats build time. |
| --- | --- |

| Anthony | Vendor recovery + IT admin + AI adoption. Vast surface area. |
| --- | --- |

Team Cards

| Anthony Armstrong Director AI 10/10 ██████████ | Mindset: Owns the transformation mandate. Capacity: Vast surface area. Needs delegation. |
| --- | --- |

| Iván Calderón Platform Lead AI 10/10 ██████████ | Mindset: Built the entire data layer. Capacity: Single point of failure. Firefighting eats build time. |
| --- | --- |

| John Nunez Ops Manager AI 8/10 ██████████ | Mindset: Shipping end-to-end skills. Capacity: WH firefighting competes with builder time. KEY CONTINGENCY RISK. |
| --- | --- |

| Carolina del Rio EDI Engineer AI 7/10 ██████████ | Mindset: Giorgio calls her an expert. Builds bots. Capacity: EDI knowledge concentrated with her. Ramping on GitHub deploys. |
| --- | --- |

| Umer Raja Compliance AI 3/10 ██████████ | Mindset: Built an agent & summary tool. Capacity: Narrow mindset. Works in isolation. Highest automation upside. |
| --- | --- |

| Erickson Dela Cruz Acceptance AI 3/10 ██████████ | Mindset: Knows AI capabilities. Consistent, reliable. Capacity: Zero hands-on AI yet. Doesn't see how it applies to his work. |
| --- | --- |

| Nica Jordan Invoicing AI 2/10 ██████████ | Mindset: Understands capabilities. Stakes are real. Capacity: Zero hands-on AI. Narrow scope. Not visible growth. |
| --- | --- |

The Ask

| 1. Training Model | Erickson & Nica join BTR with John & Carolina, daily. Treat it like 3S — continuous improvement, learning together. |
| --- | --- |

| 2. Lean AI Mindset | Start with a real problem. Build the smallest workflow that solves it. Iterate. Avoid over-engineering or waiting for 'perfect' automation. |
| --- | --- |

| 3. Contingency Planning | By Day 90, document John's WH processes so someone else can step in. Same for Iván's platform and Anthony's vendor relationships. |
| --- | --- |

Key Milestones

☐  Erickson & Nica on BTR daily (Days 1–30)

☐  EDI, VC, pipeline runbooks done (Days 1–30)

☐  Umer ships chargeback bot (Days 31–60)

☐  Erickson ships VC-tracker bot (Days 31–60)

☐  Nica ships invoice validation bot (Days 31–60)

☐  John has a documented WH backup (Days 61–90)

☐  Human-in-loop controls documented (Days 61–90)

☐  Headcount & role review (Days 61–90)

Give us 90 days.

We will move the entire team from skill-builders to AI owners, each running agents in their domain. We will document the contingencies that keep the operation running if someone leaves. And we will establish a lean-AI culture.