americanflat
Operations

A 90-Day Plan — Team AI Readiness & Development

Prepared by Kent Nunez   ·   June 2026

01 — THE SITUATION

Where we are.

Since January, the operations team has gone all-in on AI. Three team members are already building and shipping skills; three are still ramping — they understand the capability but haven't yet led an end-to-end AI workflow. The goal for the next 90 days is to move the entire team to ownership, where each person builds and operates AI agents in their domain, supported by a lean-AI mindset and clear contingency planning.

This plan is a direct, honest read on where each person is today, what holds them back, and what we will deliver. AI score: 1–3 fully manual or single-tool use  ·  4–6 regular use for analysis  ·  7–8 building & shipping skills  ·  9–10 owns the platform and unblocks others.

02 — THE CONTEXT

The environment we are operating in.

| TEAM Seven people: three builders (Anthony, Iván, John), three ramping (Carolina, Umer, Erickson, Nica). | AI MATURITY Builders drive the transformation. Ramping team members understand AI capabilities but lack hands-on ownership of an AI workflow. |
| --- | --- |
| SYSTEMS Amazon VC, Luminous, STEDI/EDI, BigQuery pipelines, Claude agents, GitHub skill-publishing infra, Slack bots. | RISK Single point of failure on John for WH operations and skill-building. Key-person concentration on Iván (platform) and Anthony (vendor recovery). |

03 — THE PLAN

Three phases. Ninety days.

| 01 Days 1–30 Stabilize Erickson and Nica join a real daily task (e.g. BTR skill) with John and Carolina. Document critical knowledge: EDI maps, data pipelines, VC workflows. | 02 Days 31–60 Systematize Each team member owns a Claude agent in their domain. Umer, Erickson, Nica ship their first end-to-end workflow. Light skill-review standard for quality gate. | 03 Days 61–90 Scale Build contingency for John (WH ops backup). Set human-in-the-loop controls for billing and acceptance (Luminous + Claude + human approval). Revisit headcount post Day 90. |
| --- | --- | --- |

04 — THE TEAM

Seven people. AI ratings and key gaps.

| PERSON & DOMAIN | MINDSET | CAPACITY / PERSONALITY |
| --- | --- | --- |
| Anthony Armstrong Director of Operations Owns AI transformation, vendor recovery, 3PL strategy AI 9 / 10 ██████████ | Owns the transformation; no one else has the bandwidth or mandate. | Capacity. Vast surface area: AI adoption, vendor contracts, IT assist, day-to-day ops. Personality. Key risk if he steps back. Needs explicit delegation and scope recognition. |
| Iván Calderón AI & Data Manager Owns data platform, GCP/BigQuery, skill-publishing infra, identity / access AI 10 / 10 ██████████ | Built the entire data layer and skill-publishing system. No one understands the platform. | Capacity. Single point of failure across infra and security. Daily firefighting eats build time. Personality. Needs documented backup and protected build time. Platform-owner mandate to route requests through systems. |
| John Nunez Ops Manager Owns WH flow, VC compliance, builds Claude skills, runs 3S-style improvement AI 8 / 10 ██████████ | Shipping end-to-end skills (Short Processor, VC-PO bot, Walmart companion). Strong practitioner. | Capacity. WH daily firefighting competes with builder time. No backup for critical WH ops. Personality. Likely reaches 10/10 after 30-day training. Key contingency risk — if John leaves, WH ops + AI building go dark. |
| Carolina del Rio People Ops & Systems Analyst Really: EDI/Integrations Engineer, automation builder, people-ops systems AI 7 / 10 ██████████ | Built the Attendance app, 940 validator, Coffee scheduler, Luminous report bot. Giorgio calls her an expert. | Capacity. Still ramping on GitHub deploys (leans on Iván); EDI knowledge concentrated in her. Personality. Needs pairing with Iván for self-sufficient deploys. Good candidate to help onboard Erickson/Nica to building. |
| Umer Raja Ops Assistant — VC Compliance Chargeback disputes (36–258/day), SIOC certification, orders reconciliation, Zendesk AI 3 / 10 ██████████ | Built an agent and summary tool; slightly above zero hands-on use. | Capacity. Narrow mindset; rigid schedule; doesn't think outside scope. Works in isolation. Personality. Needs the BTR shared-task model (daily, with others, learning by doing). High-ROI automation target; flagged as most-automatable role if headcount reduction needed. |
| Erickson Dela Cruz Ops Assistant — VC Acceptance VC order acceptance (US/EU/CN), Andon Cord complaint process, price/shortage claims AI 3 / 10 ██████████ | Knows AI capabilities from meetings. Consistent, reliable, never misses an update. | Capacity. Little hands-on AI use. Doesn't see how it applies to his repetitive VC-tracker work. Personality. Start with BTR task (daily shared model). Partner with Carolina/John. High-upside target: VC-tracker entry could be 80% automated. |
| Nica Jordan Ops Assistant — VC Invoicing VC invoicing pipeline, Invoice Recap to leadership, QB/Luminous sync, invoice validation AI 2 / 10 ██████████ | Understands capabilities; reports billed revenue to the CEO — the stakes are real. | Capacity. Zero hands-on AI use yet. Narrow scope, not visible growth. Terse comms make blockers invisible. Personality. Needs the BTR shared task to build confidence. First win: invoice validation / FCR bot. Weekly checkpoints so progress is visible. |

05 — AI OWNERSHIP MODEL

Future state. Each person owns agents in their domain.

Automation: Each team member builds and operates Claude agents in their area — VC acceptance, invoicing, chargeback disputes, EDI, warehouse operations. Agents run daily, unattended, with human sign-off on exceptions.

Human-in-the-loop controls: Billing (invoices) and acceptance (VC orders) stay under human review. Luminous + Claude do the heavy lifting; a person makes the final approval. Full automation creates unacceptable risk if that person is out.

Contingency: The biggest risk is John. If he leaves, WH operations and skill-building both go dark. By Day 90, identify a backup for his WH responsibilities and document the skill-building process so someone else can take over if needed. Same for Iván's platform and Anthony's vendor relationships.

06 — MILESTONES

What we will deliver.

| PHASE | DELIVERABLE | OWNER | MEASURE |
| --- | --- | --- | --- |
| Days 1–30 | Erickson & Nica join BTR shared task with John & Carolina | John, Carolina | Daily participation, tasks completed together |
| Days 1–30 | EDI, VC, and pipeline workflows documented | Iván, Carolina | Written runbooks; a backup can execute them |
| Days 31–60 | Umer ships chargeback / shortage dispute bot | Umer, John | First end-to-end AI workflow in production |
| Days 31–60 | Erickson ships VC-tracker entry bot | Erickson, Carolina | AI-assisted acceptance workflow live |
| Days 31–60 | Nica ships invoice validation / FCR bot | Nica, Iván | Invoicing quality checks automated |
| Days 61–90 | John has a documented WH ops backup | John, Anthony | Cross-trained person can cover basic WH ops |
| Days 61–90 | Human-in-the-loop controls (Luminous + Claude) documented | Iván, John | Process for approval gates written, tested |
| Days 61–90 | Headcount and role review | Anthony | Revisit team structure post-training; decide on Umer role |

07 — THE ASK

What I am asking for.

1. Training Model.  Let Erickson and Nica join the BTR shared task with John and Carolina, daily. Treat it like 3S — continuous improvement, everyone learning together, building real workflows, not classroom training.

2. Lean AI Mindset.  Coach the team to think 'lean AI': start with a real problem, build the smallest workflow that solves it, iterate. Avoid over-engineering or waiting for 'perfect' automation.

3. Contingency Planning.  By Day 90, document John's WH processes and skill-building approach so someone else can step in. Same for Iván's platform and Anthony's vendor relationships. The team is too concentrated.

Give us 90 days. - We will move the entire team from skill-builders to AI owners, each running agents in their domain. We will document the contingencies that keep the operation running if someone leaves. And we will establish a lean-AI culture where the team thinks in terms of small, iterative workflows, not big transformations.